## Monthly Report
MONTHLY CALENDAR - ABRA FLEET MANAGEMENT SYSTEM
Employee Name: | Asha
Department: | IT
Designation: | Software Development
Time | 01 Mon | 02 Tue | 03 Wed | 04 Thu | 05 Fri | 06 Sat | 07 Sun | 08 Mon | 09 Tue | 10 Wed | 11 Thu | 12 Fri | 13 Sat | 14 Sun | 15 Mon | 16 Tue | 17 Wed | 18 Thu | 19 Fri | 20 Sat | 21 Sun | 22 Mon | 23 Tue | 24 Wed | 25 Thu | 26 Fri | 27 Sat | 28 Sun | 29 Mon | 30 Tue | 31 Wed
09:00–10:00 | Project kickoff meeting | Complete schema design review | Wireframing session (Part 1) | Wireframing session (Part 2) | Design system definition | Weekend work - Complete mockups | WEEKLY OFF | Dashboard module kickoff | Stats cards development | Live trips table development | Activity feed development | Dashboard charts development | Dashboard polish and testing | WEEKLY OFF | Trip Management module start | Trip API integration | Trip details and mapping | Create and Update Trip | Trip status and delete | Trip module testing | WEEKLY OFF | Employee Management start | Employee CRUD operations | Employee features enhancement | Billing module development | Invoice PDF generation | Billing analytics | WEEKLY OFF | Roster Management start | Safety & SOS module | Reports, Routes & Settings
10:00–11:00 | Set up Node.js backend with Express | Design Roster schema with indexing | Create Dashboard wireframes | Create Billing module wireframes | Define color palette and typography | Roster module mockups | WEEKLY OFF | Build sidebar navigation structure | Build 6 stat card widgets | Build trips table structure | Build activity feed widget | Build Department Cost chart | Add loading states to all widgets | WEEKLY OFF | Build trip stats cards | Develop GET /api/trips endpoint | Integrate Google Maps plugin | Build Create Trip form | Implement status update feature | Test filters functionality | WEEKLY OFF | Build employee list table | Build Add Employee form | Build employee detail view | Build billing stats cards | Integrate PDF library in backend | Build Department Cost chart | WEEKLY OFF | Build roster table layout | Build SOS emergency button | Build report generation form
11:00–12:00 | Configure MongoDB Atlas database | Design Invoice schema structure | Design stats cards layout | Design Roster screen layout | Set spacing and component styles | Safety and Reports mockups | WEEKLY OFF | Create 9 menu items with icons | Design metrics display layout | Display ongoing trip details | Create Activity model | Create Trip Volume visualization | Implement error handling | WEEKLY OFF | Create filter section layout | Implement filtering logic | Build trip detail modal | Add form validation | Create status change endpoint | Test search feature | WEEKLY OFF | Create employee stats cards | Create Edit Employee form | Display trip history | Create invoice table layout | Create invoice PDF template | Create budget widget | WEEKLY OFF | Create roster creation form | Create alert history table | Create POST /api/reports/generate
12:00–13:00 | Design Employee collection schema | Create SOS Alert schema | Create live trips table wireframe | Create Safety module wireframes | Create Dashboard high-fidelity mockups | Routes and Settings mockups | WEEKLY OFF | Design top bar layout | Create dashboard stats endpoint | Create Trip model in backend | Develop recent activities endpoint | Design Cost Analysis chart | Create empty state designs | WEEKLY OFF | Design trip list table (11 columns) | Add pagination support | Display full trip information | Develop POST /api/trips endpoint | Develop DELETE /api/trips/:id | Verify pagination works | WEEKLY OFF | Develop Employee model | Develop POST /api/employees | Create employee trips endpoint | Develop Invoice model | Develop GET /api/invoices/:id/pdf | Develop billing analytics endpoints | WEEKLY OFF | Develop Roster model | Develop SOSAlert model | Build route table display
13:00–13:45 | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | WEEKLY OFF | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | WEEKLY OFF | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | WEEKLY OFF | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | LUNCH | WEEKLY OFF | LUNCH | LUNCH | LUNCH
13:45–14:45 | Design Trip and Route schemas | Configure Firebase authentication | Trip Monitoring wireframes | Reports screen wireframes | Create Trip Monitoring mockups | Build Flutter widget library | WEEKLY OFF | Add notifications feature | Implement aggregation logic | Develop GET /api/trips/live endpoint | Add Quick Actions panel | Develop chart data endpoints | Make dashboard responsive | WEEKLY OFF | Add pagination controls | Connect table to API | Create GET /api/trips/:id endpoint | Build Edit Trip form | Test all CRUD operations | Test map integration thoroughly | WEEKLY OFF | Create GET /api/employees endpoint | Create PUT /api/employees/:id | Develop GET /api/employees/:id/trips | Create GET /api/invoices endpoint | Implement download feature | Integrate analytics with API | WEEKLY OFF | Create GET /api/rosters endpoint | Create POST /api/sos endpoint | Create GET /api/routes endpoint
14:45–16:00 | Create ER diagram for all modules | Set up Firestore database | Design filter and map area layout | Routes module layout design | Employee Management screen mockups | Create reusable components | WEEKLY OFF | Create user profile section | Connect cards to API | Implement auto-refresh (30 sec) | Create navigation buttons | Implement aggregation logic | Test on multiple screen sizes | WEEKLY OFF | Implement sorting functionality | Add loading states | Display route on map | Create PUT /api/trips/:id endpoint | Verify data integrity | Verify trip tracking | WEEKLY OFF | Add search functionality | Implement photo upload | Implement DELETE employee | Add status badges | Add payment update function | Test billing analytics | WEEKLY OFF | Develop POST /api/rosters | Develop GET /api/sos endpoint | Build settings screen
16:00–16:15 | TEA | TEA | TEA | TEA | TEA | TEA | WEEKLY OFF | TEA | TEA | TEA | TEA | TEA | TEA | WEEKLY OFF | TEA | TEA | TEA | TEA | TEA | TEA | WEEKLY OFF | TEA | TEA | TEA | TEA | TEA | TEA | WEEKLY OFF | TEA | TEA | TEA
16:15–17:15 | Document schema relationships | Create Postman collection for APIs | Employee Management wireframes | Settings screen wireframes | Billing module mockups | Configure navigation routing | WEEKLY OFF | Set up routing between modules | Add loading states to cards | Test live updates functionality | Test activity feed updates | Integrate charts with APIs | Fix dashboard bugs | WEEKLY OFF | Test table interactions | Implement filter apply/reset | Test map integration | Test create functionality | Fix delete functionality | Fix identified bugs | WEEKLY OFF | Implement filter feature | Configure Firebase Storage | Test all employee features | Implement invoice filtering | Test PDF generation | Test entire billing module | WEEKLY OFF | Build employee assignment UI | Test emergency alert flow | Develop settings endpoints
17:15–18:00 | Daily standup and EOD report | Document all API endpoints | Create list and form layouts | Finalize user flow patterns | Review and refine all mockups | Set up state management | WEEKLY OFF | Test navigation flow | Test stats card functionality | Debug and optimize queries | Integrate with dashboard | Test chart rendering | Complete dashboard module | WEEKLY OFF | Review trip screen layout | Test API integration | Debug map rendering issues | Test update functionality | Complete trip CRUD testing | Optimize performance | WEEKLY OFF | Test employee list display | Test photo upload feature | Complete employee module | Test billing screen | Verify download functionality | Complete billing module | WEEKLY OFF | Test roster creation | Complete safety module | Final integration testing